## Launch Checklist
# | Area | Task | Status | Owner | Est. cost ₹ | Actual ₹ | Due date | Notes
1 | Legal | Confirm/upgrade FSSAI category (Retailer -> Trader/Marketer/Repacker) via FoSCoS 1800 112 100 | Not started | Tinku | 0 |  | 2026-10-16 | Add Marketer/repacker category; current reg 21226194003349 is Retailer only
2 | Legal | GST registration approved (Regular, not Composition, for quick-commerce) | In progress | Tinku | 0 |  | 2026-10-20 | 14 Oct: GST registration certificate (file AA291026038146B_RC14102026.pdf) emailed by Tinku to himself. GSTIN and scheme (Regular vs Composition) still to be confirmed from the certificate.
3 | Legal | Business current account (name same as GST/PAN/FSSAI) | Not started | Tinku | 0 |  | 2026-10-18 | GST certificate now available (14 Oct), so the bank application can start.
4 | Legal | Udyam (MSME) registration - free | Done | Tinku | 0 |  | 2026-10-15 | UDYAM-KR-03-0774393 registered 15 Oct 2026 (free at udyamregistration.gov.in)
5 | Legal | BBMP trade licence (physical premises address) | Not started | Tinku | 3000 |  | 2026-10-20
6 | Legal | Trademark search on IP India + file TM-A (Class 30/31) | In progress | Tinku | 4500 |  | 2026-10-16 | Secondary registry mirror: SPICO (App 1518819, Class 30, Nilesh Jain, Indore) listed Registered for snacks/namkeens/rice/flour/spices etc. Confirm on IP India Public Search; pick fallback names before printing.
7 | Sourcing | Shortlist 3 pulse suppliers & get rate quotes (APMC Yeshwanthpur) | In progress | Tinku | 0 |  | 2026-10-18 | Emailed Sri R K Traders (srirktraders1@gmail.com) and Hazalmo (info@hazalmo.com) on 13 Oct 2026 ~4:20 PM IST; awaiting replies. More APMC contacts still uncontacted.
8 | Sourcing | Sample purchase & quality check | Not started | Tinku | 2000 |  | 2026-10-20
9 | Sourcing | Select FSSAI-licensed contract repacker; get quote & agreement | Not started | Tinku | 0 |  | 2026-10-20
10 | Quality | NABL lab test for nutrition values (per product) | Not started | Tinku | 6000 |  | 2026-10-25 | Rs3k per product; 2 SKUs ~Rs6k, 4 SKUs ~Rs12k (pending SKU decision)
11 | Packaging | Finalise label (repacker details, lab values, contact, MRP) | Not started | Tinku | 0 |  | 2026-10-25
12 | Packaging | Order pouches & labels | Not started | Tinku | 12000 |  | 2026-10-27
13 | Packaging | Barcode: decide GS1 (or Blinkit exception code) before printing | Not started | Tinku | 0 |  | 2026-10-25 | GS1 on hold (~Rs50k); ask Blinkit for exception code
14 | Sales | Blinkit Seller Hub application | Not started | Tinku | 0 |  | 2026-11-12 | Hold until repacker quotes; QC MRP ~Rs229/kg at 12% margin
15 | Sales | Zepto application | Not started | Tinku | 0 |  | 2026-11-12 | Hold, as above
16 | Sales | Swiggy Instamart application | Not started | Tinku | 0 |  | 2026-11-12 | Hold, as above
17 | Sales | Identify & pitch 5 line suppliers/distributors (rate card ready) | Not started | Tinku | 1000 |  | 2026-10-31
18 | Sales | Kirana sampling in Koramangala/Jayanagar/JP Nagar/E-City/MG Road | Not started | Tinku | 3500 |  | 2026-10-31 | Marketing plan: marketing/launch_marketing_plan.md
19 | Finance | Set up billing software & opening stock | Not started | Tinku | 0 |  | 2026-10-27 | Vyapar or myBillBook
20 | Finance | Monthly GST return filing calendar | Not started | Tinku | 0 |  | 2026-10-27
21 | Decision | Launch with 2 SKUs (toor, moong) or all 4 | On hold | Tinku | 0 |  | 2026-10-14 | 13 Oct: 2-SKU choice reopened, awaiting final product list
22 | Decision | Approve Rs8,000 marketing cap (budget has Rs4,500) | Not started | Tinku | 8000 |  | 2026-10-14 | Hold public branding; pick 2-3 names for free IP India search by 16 Oct
23 | Decision | Fallback brand name if SPICO conflicts | Not started | Tinku | 0 |  | 2026-10-16 | Hold public branding
24 | Decision | Kirana intro offer level | Not started | Tinku | 0 |  | 2026-10-20 | Floor price Rs155/kg toor
25 | Decision | Regular GST vs composition scheme (confirm with CA) | Not started | Tinku | 0 |  | 2026-10-20 | Accounts recommends Regular for quick-commerce
TOTAL

## Budget
Head | Planned ₹ | Actual ₹ | Variance ₹ | Notes
Initial stock (~400 kg mixed pulses @ ~₹115/kg) | 45000 |  |  | 4 SKUs x 2 sizes; small lots from APMC
Packing pouches & labels (MOQ printed laminate/stickers) | 12000 |  |  | Start with stock pouch + printed sticker to cut MOQ
Repacking + transport (first 2 runs) | 5000
Branding: logo, label design, Legal Metrology-compliant label | 7000
GS1 barcodes (EAN) registration | 0 |  |  | Deferred: GS1 is about Rs 50,200; try Blinkit exception code first
Trademark application (TM-A, individual/startup) | 4500 |  |  | ₹4,500 govt fee for e-filing by individual/startup
Platform onboarding, photos, catalogue, lab test report | 8000 |  |  | NABL test report often requested
Kirana/line-supplier samples & local marketing | 4500
Buffer/working capital (platform payouts lag 7-30 days) | 8000
TOTAL
Available capital | 100000 |  |  | Remaining cash = capital - actual spend

## Transactions
Date | Type (Purchase/Sale/Expense) | Party | Item | Qty (kg/pcs) | Rate ₹ | Taxable ₹ | GST % | GST ₹ | Total ₹ | Payment mode | Invoice no.
Purchases
Sales
Expenses
GST paid (input)
GST collected (output)

## Inventory
SKU | Opening qty | Purchased/packed | Sold | Closing qty | Cost/unit ₹ | Stock value ₹ | Reorder level | Reorder?
Toor dal 1kg | 0 | 0 | 0 |  |  |  | 20
Toor dal 500g | 0 | 0 | 0 |  |  |  | 20
Urad dal 1kg | 0 | 0 | 0 |  |  |  | 20
Urad dal 500g | 0 | 0 | 0 |  |  |  | 20
Moong dal 1kg | 0 | 0 | 0 |  |  |  | 20
Moong dal 500g | 0 | 0 | 0 |  |  |  | 20
Chana dal 1kg | 0 | 0 | 0 |  |  |  | 20
Chana dal 500g | 0 | 0 | 0 |  |  |  | 20
TOTAL

## Suppliers
Name | Type | Area/Address | Phone | Website/Email | Source URL | Notes | Contacted? | Quote ₹/kg | FSSAI no.
ATM Pulses | Pulses wholesaler | 54C 3rd Cross, Lorry Godown St, APMC Yard, Yeshwanthpur 560022 (also Bhadra Complex 26/38 APMC Yard) | 080-41283428, 080-23185797, +91 7019615450 |  | https://www.asklaila.com/listing/Bangalore/yeshwanthpur/atm-pulses/FAILEGsJ/ | Pulses & rice; Mon-Sat 10am-8pm per exa listing
Sanghavi Agro Pulses | Pulses wholesaler | 52/2 Kirana Complex, APMC Yard, Yeshwanthpur 560022 | 080-40964549 |  | https://www.asklaila.com/listing/Bangalore/yeshwanthpur/sanghavi-agro-pulses/0TKw9xqZ/ | Toor, urad, gram dal, moong, peas
Super Traders | Rice & pulses wholesaler | 185/19/1 6th Main, APMC Yard, Yeshwanthpur 560022 | 080-41283352, 080-23470537 |  | https://www.asklaila.com/listing/Bangalore/yeshwanthpur/super-traders/khDN7tDt/ | Moong, toor, urad
Sanjay Traders | Rice & pulses wholesaler | 173 6th Main, APMC Yard, Yeshwanthpur 560022 | 080-41283225 |  | https://www.asklaila.com/listing/Bangalore/yeshwanthpur/sanjay-traders/IPCOTA8q/ | Bengal gram dal, urad, toor, green gram
Taj Agencies | Pulses wholesaler | 206/1 6th Main, APMC Yard, Yeshwanthpur | 080-41283301, 080-23374215 |  | https://www.asklaila.com/listing/Bangalore/yeshwanthpur/taj-agencies/1lG1C9lC/ | From search summary; verify listing
Sri R K Traders | Wholesale grocery incl. dals | 57/4-57/5 B.R. Complex, 5th Main, Lorry Godown St, APMC Yard, Yeshwanthpura 560022 | +91 87489 35819 (WhatsApp) | srirktraders.in / srirktraders1@gmail.com | https://srirktraders.in/ | Same-day delivery nearby if ordered before 2 PM; good for small trial lots | Yes - email 13 Oct 2026 | Awaiting reply
Advith Enterprises | Organic toor/chana dal supplier | 273 6th Cross, KHB Colony, Magadi, Ramanagara 560060 | (not shown; site chat) | advithenterprises.co.in | https://www.advithenterprises.co.in/ | Contacts: Avinash & Shankara K B; est. 2024
Hazalmo Exports | Toor dal (unpolished/polished) sourcing & packing | 108A Samprasiddhi Green Edge, Rachenahalli, Bangalore 560077 | +91 9353101164, +91 9632842231 | info@hazalmo.com | https://hazalmo.com/toor-dal/ | Exporter; offers unpolished option (premium positioning) | Yes - email 13 Oct 2026 | Awaiting reply
Sri Ranganatha Industries | Manufacturer (Peenya) | 2nd Block, Peenya 1st Stage, Leggere Rd 560058 | +91 9448344651 |  | https://exa.ai/library/places?q=c0d8cd7a0e64e04a | Appeared in dal-mill search; product line not confirmed - verify
Krupaa Foods | Dal manufacturer/processor (toor, chana, urad, moong) | Location not confirmed on page | (not shown) | krupaafoods.com | https://krupaafoods.com/ | Verify it is Karnataka-based before contacting
Indian Pulses | Pulses trader/wholesaler (IndiaMART) | Bengaluru | (via IndiaMART) |  | https://www.indiamart.com/company/143301004/indian-pulses.html | Green peas & pulses
Bangalore Wholesale Food Grains & Pulses Merchants Association | Trade association | APMC Yeshwanthpur area | (not captured) |  | search summary (IndiaMART/AskLaila results) | Good route to get a member list of APMC dal traders
Mudga Industries Pvt Ltd | Commodity repacking, private/white label | Bengaluru North Taluk | +91 9663897366, 6366166565 | mudgaindustries.com | https://mudgaindustries.com/ | All dals; also FSSAI/labelling consultancy; NPOP organic certified
Nova Packaging Company | Food contract packing (dals, spices) | Shankarappa Indl Estate, Magadi Main Rd, Sunkadakatte 560091 | 07942560683 (IndiaMART virtual no.) | novapacks.in | https://www.novapacks.in/contract-packaging-services.html | Prop. Vinod Kumar S.B.; listed 'Rs 1/piece' (price on request); also coding/printing. FSSAI not stated - ask
Jyothi Packers | Grocery/pulse packing + delivery | Yeshwanthpur | (via ExportersIndia) | jyothipackers.co.in | https://www.exportersindia.com/product-detail/packing-food-commodity-5036316.htm | Pulse machine ~8 t/shift; 1-10kg semi-auto; also delivers to shops
Pure Products (Isleworth Tradelinks Ltd) | Private label & contract mfg, FSSAI/ISO22000/HACCP | 26 2nd Main, Konnenna Agrahara, Murgeshpalya 560017 | (via ExportersIndia) | pureproducts.co.in | https://www.exportersindia.com/pureproducts/manufacturing-services.htm | End-to-end for startups incl. label design, sourcing
RG Packaging (Raval Group) | Repacker/co-packer, VFFS pouch packing | Location to verify | (see site) | rgpackaging.in | https://rgpackaging.in/ | Grains & pulses; confirm Bangalore unit & FSSAI